PROJECT PLANNING DOCUMENTATION

Project planning establishes the formal development roadmap, tracking matrices, task estimations, and timeline controls utilized to implement the Online Complaint Registration System systematically. By applying Agile software engineering paradigms, the execution lifecycles are monitored through quantifiable story metrics to assure strict alignment with academic delivery thresholds.

# 1. Product Backlog & Task Breakdown

The system requirements are decomposed into discrete, manageable functional tasks within a single engineering backlog. Each backlog item is isolated by component layer to map development paths directly to core implementation structures:

| Module ID | Backlog Item Module | Engineering Task Breakdown Description | Effort (SP) |
| --- | --- | --- | --- |
| BK-101 | Database Infrastructure | Initialize MongoDB service clusters, model User and Complaint collection BSON validation constraints, and register connection pooling drivers. | 12 SP |
| BK-102 | Security Controllers | Develop cryptographic password salting utilities and build the JSON Web Token (JWT) route guard server interceptor middleware layers. | 16 SP |
| BK-103 | User Interfaces (UI) | Construct responsive single-page layouts in React, instantiate core forms with automated format checking, and wire asynchronous routing states. | 18 SP |
| BK-104 | Integration & Testing | Conduct cross-origin communication checkups, wire administrative state triggers, and perform comprehensive validation routines. | 14 SP |

# 2. Sprint Planning & Milestone Schedules

To implement features across manageable intervals, development milestones are scheduled into four distinct, time-boxed sprint checkpoints spanning an 8-week developmental horizon.

| Timeline Checkpoint | Estimated Backlog Effort (Story Points) | Actual Remaining Backlog Effort (Story Points) | Velocity Variance Summary % |
| --- | --- | --- | --- |
| Project Start (Day 0) | 60 SP | 60 SP | 0.0% Initialized |
| Sprint 1 Finish (Day 14) | 45 SP | 43 SP | +3.3% (Ahead of Schedule) |
| Sprint 2 Finish (Day 28) | 30 SP | 28 SP | +4.4% (Ahead of Schedule) |
| Sprint 3 Finish (Day 42) | 12 SP | 15 SP | -5.0% (Slight CORS Intercept Delay) |
| Sprint 4 Finish (Day 56) | 0 SP | 0 SP | 0.0% (Milestone Met Successfully) |

- Sprint 1 (Weeks 1-2): Core Database Architecture — Focused entirely on data storage initialization, setting up connection configurations, collection indexing, and setting up backend multi-tier project directories.

- Sprint 2 (Weeks 3-4): Security Validation Engine — Dedicated to establishing secure pathways, writing stateless session modules, hashing routines, and building role-based access controls (RBAC) to insulate routes.

- Sprint 3 (Weeks 5-6): Interactive Client Views — Comprises front-end user experience developments, component designs for forms, tracking grids, and client-side page state checking rules.

- Sprint 4 (Weeks 7-8): Quality Assurance & Staging — Features system cross-tier assembly, connection validation, error troubleshooting, and finalizing localized deployment scripts.

# 3. Performance Metrics: Velocity Tracking & Burndown Analysis

Project team speed and feature progression variables are quantified through a standardized Story Point metrics table tracking intended timelines against actual development outputs:Burndown Analysis Justification

The task metrics evaluate project velocity as stable and reliable across the timeline. The small effort deflection observed during the completion checkpoint of Sprint 3 relates directly to Cross-Origin Resource Sharing (CORS) connection parameters that surfaced when testing asynchronous API fetches between decoupled browser channels and backend port gateways. Adjusting communication routing setups during Sprint 4 recovered this minor schedule deviation, concluding all core milestones securely on time.